Microsoft Enterprise Project Management (EPM)

Overview and Configuration Guidance

Documentation for

JT3

Author: S. Wagner

Version: Draft

Date: 6/18/2007

Requirements and Configuration Specification V.1.0

# Table of Contents

Table of Contents	2

Core Requirements	3

Process Improvement Requirements and Goals	3

Deployment Scope	3

Project Definition	3

Project Organization	3

Project Characteristics	3

Task Characteristics	3

Resource Characteristics	3

Working Times and Calendars	3

Project Tracking Methods and Options	3

Security Requirements	3

Training Requirements	3

Project Templates	3

Project Files/Data	3

Library Customizations	3

Issues Customizations	3

Menu Customizations	3

Project Guide Customizations	3

Custom Gantt Chart Formats	3

Custom Grouping Formats	3

System Design Information	3

Notifications	3

Windows SharePoint Services Configuration	3

Homepage links and content additions	3

Project Views	3

Project Web Access Views	3

Custom Filters	3

Web Site Information	3

General Configuration Requirements	3

Custom Field Definitions	3

Application Account Information:	3

Server Configuration Requirements	3

# Current Status

JT3 currently has a Microsoft Enterprise Project Management (EPM) 2003 test Solution deployed called MOPS in a Box. MSProjectExperts has been retained to provide guidance and suggest best practices to ease the implementation and adoption of this solution within JT3.

## Deployment Requirements and Goals

- Define and Refine process to meet the tool needs

- Assign Application Administration role

- Develop and refine project templates

- Begin initiating projects from templates

- Manage organizational change within the tool

- Create management and executive views and reports based on EPM data

- Requirements listed in EPMS List of Requirements Document

- Recommend and or confirm hardware and software requirements

## Noted Observations

- Executive Buy-In and direction will be key to a successful implementation at JT3

- Cultural Adoption is a serious opportunity within JT3

JT3 must be able to present a cohesive strategy to executives and management and obtain the buy-in and support of both executives and upper management. Implementing a training and demo instance on the currently allocated production hardware will serve to help with both needs above. A training strategy must be implemented by PWA role to ease adoption.

SharePoint Services 2.0 should be used to help with adoption. The SharePoint product has been proven to lend itself to quick adoption. Both SharePoint and Project Web Access (PWA) should be branded with JT3 colors and logos to help ease adoption.

While most of the requirements in the EPMS List of Requirements document can be met by product configuration, some of the future requirements and a need to push information rather than have users pull information from this solution leads MSProjectExperts to recommend the added product SQL Reporting Services to the list of EPM products.

Discussion on Specific Portfolio, Project and resource fields is ongoing and a list of those recommended fields will be presented in this final document.

Note: Per requirements many items are TBD by client.

## Project Organization

| Requirement | Value |
| --- | --- |
| Total number of active projects to accommodate | 100 per year |
| Near future number if deployment expansion is a near-term goal | 200 |
| Average project size in number of tasks | 500 |
| Largest expected project in number of tasks | 1500 |
| Average project duration (can be expressed in elapsed time or duration units and note which method you are using) | 12 Months |
| Longest anticipated project duration (can be expressed in elapsed time or duration units and note which method you are using) | 24 Months |
| External dependencies will be used (Y/N) Explain. | N |
| Earned Value method used (physical, work, N/A) | Y |
| Total number of system users | 1300 |
| Total number of human resources | 1300 |
| Total number of other work resources | 200 |
| Total number of material resources | 200 |
| Does the company span multiple locations? (If yes, provide details) | Yes – No Remote access on same LAN |
| Do projects span multiple locations? (If yes, describe control structure and resource sharing plan) | Yes, None Matrix |
| Do location codes exist? | No |
| Will Project Professional users span multiple locations? | No |
| Will Project Web Access users span multiple locations? | Future Maybe |
| Single locale or MUI Installation? | Single |
| Are Master Projects allowed? (If yes, explain management strategy) | Yes, Not Published |
| Will the system specify a single currency setting? (If yes, provide) | Yes $ |
| Will Project Managers be allowed to use local base calendars? | No |
| Define date range for long-range resource availability information. | 12 Months |
| Define date range for OLAP information and frequency of update. | 12 Months |
| Who will be responsible for maintaining resource data? | Administrator |
| Who will be responsible for maintaining project artifacts? | PM’s |
| Who is responsible for updating resource calendar data? | Resource Managers – Admins at first |
| Authentication method for the Project Server | Windows |
| Minimum Password Length | NA |
| Require Server authentication prior to publishing (Y/N) | Y |

## Project Characteristics

| Requirement | Value |
| --- | --- |
| Describe project life-cycle phases and the importance of these to management reporting. | Modified PMI Very |
| Is there a corporate project numbering system (If yes, specify) | Yes – Unique ID Code |
| Are there accounting codes that are applied at the project level? (If yes, specify) | Future? |
| Are individual projects aggregated into programs supporting related initiatives? (If yes, describe) | Yes |
| Are programs aggregated into multiple portfolios? (If yes, describe) | No |
| Are projects identified by client or consumer entity? (If yes, describe) | No |
| Describe other unique identifiers for projects that may be required for reporting or interfaces with other host applications that may apply | Department, Functional Manager, Resource Manager, Program |
| Describe informational fields to be maintained at the project level |  |
| Is there a need for archived versions of projects in the data store? (If yes, describe) | No |

## Task Characteristics

| Requirement | Value |
| --- | --- |
| Are there job codes or accounting codes associated with tasks? (If yes, describe) | No – Future? |
| Typical Default task type |  |
| Is task scheduling effort driven? | Yes |
| Unique WBS used? (If yes incorporate description) | No |
| Describe other unique identifiers for tasks | Budget Ind, Schedule Ind |

## Resource Characteristics

| Requirement | Value |
| --- | --- |
| Will the RBS be implemented? (If yes, provide RBS definition) | Yes |
| Are rate tables required? (If yes, provide rate table definitions) | Yes |
| Describe other unique identifiers for Resources |  |
| Are skill sets currently defined for resources? (If yes, describe) | No Roles |
| Do location attributes apply to resources? | No |
| Describe other attributes that target resource selection. | Reports To, Department, Resource Manager |
| Describe ways that resources are categorized in the company for reporting, management, and accounting purposes. | As above |
| Describe source or sources for Resource data | Manual |

## Working Times and Calendars

| Requirement | Value |
| --- | --- |
| Describe the default working times for your company | 4x10, 5X8 |
| Describe additional calendars required for implementation (Tasks) |  |
| Describe additional calendars required for implementation (Resources) |  |
| Are resource units adjusted to account for non-project time in scheduling? (If no, describe calendar method) | Yes |
| Describe Resource vacation management strategy | Admin Time |

## Project Tracking Methods and Options

| Requirement | Value |
| --- | --- |
| Enforce single tracking method? | Yes |
| Specify default tracking method | Hours/Day |
| Manage Time periods (Y/N) (Specify if yes). | Bi Weekly |
| Timesheet Approvals (Y/N) (Specify if yes) | No |
| Define default start day of a week | Monday |
| Task/Time sheets span weekly or monthly periods? | Week |
| If weekly, how many weeks should display in the timesheet? | 2 |
| If monthly, how many reporting periods in a month? (Up to three may be defined, specify start and stop parameters for all specified) |  |
| Time entries are made by the day, by the week, or by the time period. | Day |
| Maximum number of hours a resource may report in a given day. | 16 |
| Current tasks are defined as tasks that start up to how many days from the current date? | 30 |
| Non-project time collected? (If yes, specify categories) | Yes |
| 2003 Admin Projects implemented (Y/N) (If yes specify strategy) | Yes – Departmental |
| Project related administrative work collected? (Y/N) If yes specify strategy) | Yes |
| Specify migration strategies if moving from 2002 | NA |

## Security Requirements

| Requirement | Value |
| --- | --- |
| Define who has access to all project data across the enterprise. | Admin |
| By role, Describe the criteria by which an Executive, Project Manager, Resource Manager, Team Lead, or Resource has access to project data. | Default |
| By role, Describe the criteria by which an Executive, Project Manager, Resource Manager, Team Lead, or Resource has access to resource data. | Default |
| Define special roles of internal or extranet users and the data access they should have. | Default |
| Create “My Org for Team Members” category to give team members access to non-cost Project Center views for projects to which they are assigned. | Default |

## Training Requirements

Pilot Phase Requirements:

| Requirement | Value |
| --- | --- |
| Technical Administrators | 2 |
| Project Office Administrators | 0 |
| Project Manager | 0 |
| Team Member | 0 |
| Team Leader | 0 |
| Resource Manager | 0 |
| Executive | 0 |
| Other Custom | 0 |

## Project Templates

TBD. Client to define

## Project Files/Data

TBD. Client to define

## Library Customizations

TBD. Client to define

## Issues Customizations

TBD. Client to define

## Menu Customizations

None for pilot

## Project Guide Customizations

TBD. Client to define

## Custom Gantt Chart Formats

TBD. Client to define

## Custom Grouping Formats

TBD. Client to define

# System Design Information

## Notifications

| Requirement | Value |
| --- | --- |
| From Address. | TBD |
| Company Email address. | TBD |
| SMTP Server | TBD |
| SMTP Port | 25 |
| Daily run time | 0:00 |

## Windows SharePoint Services Configuration

| Requirement | Value |
| --- | --- |
| SharePoint Server name |  |
| Port # |  |
| Administration Port # |  |
| SSL Port | 443 NA |
| Database Server name |  |
| Database name |  |
| Set server to automatic or manual subweb creation? |  |
| Automatically or manually add users to subwebs? |  |
| Automatically add users to Public Documents subweb Project manager role |  |

## Homepage links and content additions

| Requirement | Value |
| --- | --- |
| Specify URLs to add |  |
| Specify Content links to add |  |

## Project Views

| View Name | Fields | Description |
| --- | --- | --- |

## Project Web Access Views

| View Name | Fields | Description |
| --- | --- | --- |
| -work – Project Center |  | Standard project view with all XX custom Enterprise Project codes and fields added |
| -cost – Project Center |  | Standard project view with all XX custom Enterprise Project codes and fields added |
| -tracking – Project Center |  | Standard project view with all XX custom Enterprise Project codes and fields added |
| -summary – Project Center |  | Standard project view with all XX custom Enterprise Project codes and fields added |
| -resource summary – Resource Center |  | Standard resource view with all XX custom Enterprise Resource codes and fields added |
| – Major Milestones – View a Project |  | Displays only milestones that are marked as major milestones |

## Custom Filters

| Filter Name | Description |
| --- | --- |

# Web Site Information

| Web Site | Port | Virtual Dir | Physical Path | Notes |
| --- | --- | --- | --- | --- |
| Default | 80 |  |  |  |
| Default | 80 | MSADC |  |  |
| Default | 80 | ProjectServer |  |  |
| Default | 80 | PSTraining |  |  |
| WSS | 81 | wss |  |  |
| WSS Admin | TBD |  |  |  |

## General Configuration Requirements

| Requirement | Value |
| --- | --- |
| Project Server Intranet URL |  |
| Project Server Extranet URL |  |

## Custom Field Definitions

| Project |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | EPOC01 | Y |  |  |  |
|  | EPOC02 | Y |  |  |  |
|  | EPOC3 | Y |  |  |  |
|  | EPTX03 |  | Shows yellow when late by one to ten days, shows red when late more than 10 days |  | Displays graphical indicator for schedule status IIf([Baseline Finish]>54789,"No Baseline",IIf([Finish Variance]/480>=10,"Late by more than 10 days",IIf([Finish Variance]/480>0,"Late","On schedule"))) |
| Resource |  |  | Continued on next page |  |  |
| Department |  |  |  |  |  |
| Role | EROC02 | Y |  |  |  |
| Task |  |  |  |  |  |
| Schedule Ind | ETTX01 |  | Shows yellow when tasks are one to ten days late, shows red when late more than ten days late |  |  |
| Major Milestone | ETFL01 |  | Y = Is Major N = Is Minor |  |  |
|  | ETOC01 |  |  |  |  |

# Application Account Information:

| Account Name | Logon | PW | Member | Description/Notes |
| --- | --- | --- | --- | --- |
| OLAP administrator |  |  | OLAP Administrators group on SQL/Analysis Services Server | OLAP Admin application account used by Project Server to connect to Analysis Services and perform cube administration through DCom object |
| WSS administrator |  |  | Local Administrators Group on Project Server/WSS Server | WSS Admin application account used by Project Server to connect to Windows SharePoint Services and peform administration through DCom object. |
| MSProjectUser |  |  | MSProject Role Note: Installation process creates role | Created automatically by installation process using password provided |
| MSProjectServerUser |  |  | MSProjectServer Role | Created automatically by installation process using password provided |
| SA |  |  | System Roles: Security Administrators DB Creators | Use built-in Account |

## Server Configuration Requirements

| Server Net Bios Name | OS | SP | Configuration | Notes |
| --- | --- | --- | --- | --- |
|  | 2003 Std |  | ProjectServer, WSS for Project Server |  |
|  | 2003 Std |  | SQL Analysis Services |  |